## TransactionData
TaskNumber | Application | Username | UserEmail | Status | StartTime | EndTime | ErrorMessage
AS400 for now

## Workflows
System | Name | Purpose | Input | Output | Comments | Effort SA | Technology | Complexity | Development | Testing | Effort Dev | Revised Effort
Misc | Test | Test | in_NotificationsFile | out_dt_Notifications | Load the notifcations | 3 | Business logic (no app.) |  |  |  |  | 3
[5 empty] | Development | 3 | [5 empty] | 3

## Reference (hidden)
Task | Owner | Simple | Low | Medium | High | Highlights | Complexity
4. Solution Design |  | 6 | 9 | 16 | 24 |  | Complexity | Development | Unit Testing | Total effort
4.02. Review PDD with developer and Support Team | Business Analyst | 1 | 2 | 4 | 6 |  | Very simple (<=5 steps) | 2 | 0.5 | 2.5
4.03. Review DSD with developer and Support Team | Solutions Architect | 1 | 1 | 1.5 | 2 |  | Simple (6-10 steps) | 4 | 1 | 5
4.06. Process walkthrough | Developer | 2 | 4 | 8 | 12 |  | Medium (11-15 steps) | 6 | 1.5 | 7.5
4.07. Define project estimates | Developer | 0.5 | 0.5 | 1 | 1.5 |  | High (16-20 steps) | 8 | 2 | 10
4.08. Review estimates with the Solutions Architect | Developer | 0.5 | 0.5 | 0.5 | 1 |  | Very high (21-25 steps) | 12 | 3 | 15
4.09. Review estimates with the SCRUM Master | Developer | 0.5 | 0.5 | 0.5 | 1 |  | Extremely complex (> 25 steps) | 16 | 4 | 20
4.13. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5 |  | Reused | 1 | 0.5 | 1.5
5. Build RPA Solution (1st pass) |  | 50.6 | 116.15 | 194.35 | 319.7
5.01. All relevant ards in Monday.com are complete | Developer | 44 | 101 | 169 | 278 | Includes coding, unit testing and integration testing
5.03. End-to-end testing is complete | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time | Multipliers
5.06. Code review is complete | Developer | 2.2 | 5.05 | 8.45 | 13.9 | 5% of the original development time | Type | Multiplier
6. UAT (1st pass) |  | 5.9 | 11.6 | 19.4 | 32.3 |  | Business logic (no app.) | 0.75
6.03. All test cases were completed | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time | Standard app. | 1
6.04. Test results tracked | Developer | 0.5 | 0.5 | 1 | 2 |  | Complex app. | 1.25
6.06. Process execution time was benchmarked | Developer | 0.5 | 0.5 | 1 | 2 |  | Java | 1.25
6.09. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5 |  | Citrix\RDP | 1.5
5. Build RPA Solution (2nd pass) |  | 20.44 | 35.26 | 56.94 | 89.28 |  | Terminal\Console | 1.5
5.01. All relevant ards in Monday.com are complete | Developer | 8.8 | 20.2 | 33.8 | 55.6 | 20% of the original development time | Image recognition | 1.5
5.02. Latest code pushed to GitHub | Developer | 0.5 | 0.5 | 0.5 | 0.5
5.03. End-to-end testing is complete | Developer | 1.76 | 4.04 | 6.76 | 11.12 | 20% of the 2nd. development time
5.06. Code review is complete | Developer | 0.88 | 2.02 | 3.38 | 5.56 | 10% of the 2nd. development time
5.07. SDD is up-to-date | Developer | 4 | 4 | 6 | 8
5.09. Exception SOPs were created | Developer | 4 | 4 | 6 | 8
5.10. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
6. UAT (2nd pass) |  | 6.9 | 12.6 | 21.4 | 34.3
6.03. All test cases were completed | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time
6.04. Test results tracked | Developer | 0.5 | 0.5 | 1 | 2
6.06. Process execution time was benchmarked | Developer | 0.5 | 0.5 | 1 | 2
6.08. Robot execution video | Developer | 1 | 1 | 2 | 2
6.09. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
7. Go Live |  | 5 | 5.5 | 9.5 | 9.5
7.03. Deployment guide was completed | Developer | 2 | 2 | 4 | 4
7.04. Accounts stored in PMP | Infrastructure Team | 0.5 | 1 | 1 | 1
7.06. Assets and queues created in Orchestrator | Developer | 1 | 1 | 2 | 2
7.07. Packages and libraries uploaded to Orchestrator | Developer | 0.5 | 0.5 | 1 | 1
7.08. Triggers created in Orchestrator | Developer | 0.5 | 0.5 | 1 | 1
7.12. Information uploaded to MS Teams | Developer | 0.5 | 0.5 | 0.5 | 0.5
8. Transition to support |  | 6.9 | 13.6 | 22.4 | 34.3
8.01. Validate process is stable | Developer | 4.4 | 10.1 | 16.9 | 27.8 | 10% of the original development time
8.02. Transition session coordinated with Support Team | Developer | 0.5 | 0.5 | 0.5 | 0.5
8.06. Code walkthrough | Developer | 1 | 2 | 3 | 4
8.07. Exception SOPs review | Developer | 1 | 1 | 2 | 2
Meetings |  | 9 | 18 | 30 | 48 | 3 hours per week
Total |  | 110.74 | 221.71 | 369.99 | 591.38